## Sheet1
Week | GitHUb | Azure Pipeline
2020-10-01 | Create repo and git clone with azure | create service connection
2020-10-08 | change python version to 3.7 and run make all | test service connection
2020-10-15 | create web app azure service | create new agent and set up local machine to work as server
2020-10-22 | run make predict and make sure everything is fine | create pipline
2020-10-29 | create locust python file | do enhancement on pipline
2020-11-05 | run locust file | do some changes in app.py and check if the pipeline deploy this change or not
2020-11-12 | test our web app | check the quality
2020-11-19 | test the quality of codes | do enhancement on pipline
2020-11-26 | do enhancement | roll back of we need
2020-12-03 | roll back of we need | do enhancement on codes
2020-12-10 | do enhancement | do enhancement
2020-12-17 | do enhancement | do enhancement
| Goals | Goals
| Create repo and git clone with azure | create service connection
| change python version to 3.7 and run make all | create nre agent on local machine
| create web app azure service | create pipline
| run make predict and make sure everything is fine | depoly a change on web app azure